## Gantt
[9 empty] | Baseline |  | Plan |  |  |  |  | 2024-08-01 |  |  |  |  | 2025-01-01
# | Alert | Project / Version / Ticket | Key | Type | Assignee | Units | Priority | Status | Start | Finish | Start | Finish | Days | % Done | Due Date | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01
1 |  | Phish Net |  | Project | [6 empty] | 2024/08/30 | 2025/02/28 | 131 | 36%
1-18 |  | Stakeholder Feedback | ANEXAS-11 | Task | Ali Zaman Kayani | 100% | Medium | In Progress |  |  |  |  | 0 | 0% | 2025-06-30
1-19 |  | Development - Cyber End | ANEXAS-90 | Epic | Umar Waqar | 100% | Medium | In Progress |  |  |  |  | 0 | 0% | 2025-07-20
1-19-1 |  | Go Phish | ANEXAS-91 | Task | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-20 |  | Template #7 - Final Presentation | ANEXAS-96 | Task | Ali Zaman Kayani | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-05-10
1-21 |  | Stakeholder Meetings - FYP Part-II | ANEXAS-98 | Epic | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-12-18
1-1 |  | Starting | ANEXAS-38 | Epic | Ali Zaman Kayani | 100% | Medium | Done |  |  | 2024/08/30 | 2024/09/02 | 2 | 100% | 2025-02-01
1-2 |  | Requirement Study | ANEXAS-33 | Epic | Ali Zaman Kayani | 100% | Medium | Done |  |  | 2024/09/02 | 2024/09/06 | 5 | 100% | 2025-02-06
1-10 |  | Feasibility Study | ANEXAS-34 | Epic | Ali Zaman Kayani | 100% | Medium | Done |  |  | 2024/09/09 | 2024/09/11 | 3 | 100% | 2025-02-03
1-3 |  | Resource Allocation | ANEXAS-35 | Epic | Ali Zaman Kayani | 100% | Medium | Done |  |  | 2024/09/12 | 2024/09/13 | 2 | 100% | 2025-02-07
1-4 |  | Team Meeting - Role & Responsibilities | ANEXAS-36 | Epic | Ali Zaman Kayani | 100% | Medium | Done |  |  | 2024/09/16 | 2024/09/20 | 5 | 100% | 2025-02-08
1-5 |  | Stakeholder Meetings - FYP Part-I | ANEXAS-37 | Epic | Ali Zaman Kayani | 100% | Medium | Done |  |  | 2024/09/23 | 2024/09/30 | 6 | 0% | 2025-06-30
1-5-1 |  | Template #1 - Project Supervisor | ANEXAS-41 | Task | Ali Zaman Kayani | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-02-14
1-5-2 |  | Template #2 - Initial Proposal | ANEXAS-42 | Task | Ali Zaman Kayani | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-02-21
1-5-3 |  | Template #3 - Proposal Presentation | ANEXAS-43 | Task | Ali Zaman Kayani | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-02-27
1-5-4 |  | Template #5 - Detailed Proposal | ANEXAS-44 | Task | Ali Zaman Kayani | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-03-20
1-5-5 |  | Template #6 - Final Proposal | ANEXAS-45 | Task | Ali Zaman Kayani | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-03-30
1-5-6 |  | Template #5 - Detailed Proposal - Iterations (if any) | ANEXAS-46 | Task | Ali Zaman Kayani | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-03-22
1-5-7 |  | Template #4 - Updated Proposal | ANEXAS-47 | Task | Ali Zaman Kayani | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-03-14
1-11 |  | Development - Front End | ANEXAS-32 | Epic | Umar Waqar | 100% | Medium | Done |  |  | 2024/10/01 | 2024/10/25 | 19 | 7% | 2025-06-30
1-11-1 |  | Registration Page | ANEXAS-1 | Task | Umar Waqar | 100% | Medium | Done |  |  |  |  | 0 | 100% | 2025-03-08
1-11-2 |  | Dashboard Functionalities | ANEXAS-2 | Task | Umar Waqar | 100% | Medium | Done |  |  |  |  | 0 | 100% | 2025-03-18
1-11-3 |  | Phishing Email Template | ANEXAS-3 | Task | Umar Waqar | 100% | Medium | Done |  |  |  |  | 0 | 100% | 2025-03-30
1-11-4 |  | Login Page | ANEXAS-48 | Task | Umar Waqar | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-03-04
1-11-5 |  | Registration Mechanism | ANEXAS-49 | Task | Umar Waqar | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-03-08
1-11-6 |  | Dashboard Page | ANEXAS-50 | Task | Umar Waqar | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-03-12
1-11-7 |  | User Spectation | ANEXAS-51 | Task | Umar Waqar | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-04-10
1-11-7-1 |  | User Spectation Dashboard | ANEXAS-62 | Subtask | Ali Zaman Kayani | 100% | Medium | Done |  |  |  |  | 0 | 0%
1-11-7-2 |  | User Roadmap | ANEXAS-72 | Subtask | Ali Zaman Kayani | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-08-27
1-11-7-3 |  | User Privileges | ANEXAS-73 | Subtask | Ali Zaman Kayani | 100% | Medium | In Progress |  |  |  |  | 0 | 0% | 2025-07-25
1-11-8 |  | Education | ANEXAS-52 | Task | Umar Waqar | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-07-31
1-11-8-1 |  | Content | ANEXAS-57 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-8-2 |  | Templates | ANEXAS-58 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-8-3 |  | Modules | ANEXAS-59 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-08-05
1-11-8-4 |  | Videos | ANEXAS-60 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-07-31
1-11-8-5 |  | MCQs | ANEXAS-61 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-08-15
1-11-9 |  | Training | ANEXAS-53 | Task | Umar Waqar | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-07-31
1-11-9-1 |  | Phishing Simulations | ANEXAS-63 | Subtask | Ali Zaman Kayani | 100% | Medium | In Progress |  |  |  |  | 0 | 0%
1-11-9-2 |  | Exams | ANEXAS-64 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-9-3 |  | Tests | ANEXAS-65 | Subtask | Ali Zaman Kayani | 100% | Medium | In Progress |  |  |  |  | 0 | 0%
1-11-9-4 |  | Videos | ANEXAS-66 | Subtask | Ali Zaman Kayani | 100% | Medium | In Progress |  |  |  |  | 0 | 0% | 2025-07-31
1-11-9-5 |  | Content | ANEXAS-67 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-9-6 |  | Templates | ANEXAS-68 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-08-04
1-11-9-7 |  | Modules | ANEXAS-69 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-9-8 |  | Quiz Manager | ANEXAS-70 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-08-29
1-11-9-9 |  | Training Manager | ANEXAS-71 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-10 |  | Testing | ANEXAS-54 | Task | Umar Waqar | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-07-31
1-11-10-1 |  | Phishing Simulations | ANEXAS-74 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-08-17
1-11-10-2 |  | Phishing Templates | ANEXAS-75 | Subtask | Ali Zaman Kayani | 100% | Medium | In Progress |  |  |  |  | 0 | 0% | 2025-08-21
1-11-10-3 |  | Modules | ANEXAS-76 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-10-4 |  | Records | ANEXAS-77 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-08-31
1-11-11 |  | User Account | ANEXAS-55 | Task | Umar Waqar | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2025-05-30
1-11-11-1 |  | Testings | ANEXAS-78 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-11-2 |  | Trainings | ANEXAS-79 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-11-3 |  | Education | ANEXAS-80 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-11-4 |  | Courses | ANEXAS-81 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-11-5 |  | Certificates | ANEXAS-82 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-08-19
1-11-11-6 |  | Privileges | ANEXAS-83 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-12 |  | Reporting | ANEXAS-56 | Task | Umar Waqar | 100% | Medium | In Progress |  |  |  |  | 0 | 0% | 2025-07-31
1-11-12-1 |  | Monthly Overviews | ANEXAS-84 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-08-20
1-11-12-2 |  | Start & End Alerts | ANEXAS-85 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-11-12-3 |  | Notifications | ANEXAS-86 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-08-15
1-11-12-4 |  | Reports | ANEXAS-87 | Subtask | Ali Zaman Kayani | 100% | Medium | In Progress |  |  |  |  | 0 | 0% | 2025-08-18
1-11-12-5 |  | Alerts | ANEXAS-88 | Subtask | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-08-13
1-12 |  | Development - Back End | ANEXAS-31 | Epic | Umar Waqar | 100% | Medium | In Progress |  |  | 2024/10/25 | 2024/11/29 | 26 | 0% | 2025-07-25
1-12-1 |  | Integration | ANEXAS-89 | Task | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-12-2 |  | Database | ANEXAS-93 | Task | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-12-3 |  | Remote Storage | ANEXAS-94 | Task | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-13 |  | Quality Asssurance | ANEXAS-27 | Epic | Umar Waqar | 100% | Medium | In Progress |  |  | 2024/12/02 | 2024/12/06 | 5 | 0% | 2025-07-30
1-13-2 |  | Usability & Efficiency | ANEXAS-95 | Task | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-13-1 |  | Quality of Life Improvements | ANEXAS-25 | Task | umar.waqar | 100% | Medium | In Progress |  |  | 2024/12/02 |  | 0 | 0% | 2025-12-01
1-14 |  | Quality Control | ANEXAS-28 | Epic | Umar Waqar | 100% | Medium | In Progress |  |  | 2024/12/09 | 2024/12/16 | 6 | 0% | 2025-08-10
1-14-1 |  | Quality Control | ANEXAS-7 | Task | Ali Zaman Kayani | 100% | Medium | To Do |  |  | 2024/12/09 |  | 0 | 0% | 2025-12-01
1-17 |  | Compliances | ANEXAS-12 | Epic | Ali Zaman Kayani | 100% | Medium | To Do |  |  | 2024/12/17 | 2024/12/20 | 4 | 0% | 2025-08-30
1-17-1 |  | Governance Compliance | ANEXAS-14 | Task | Ali Zaman Kayani | 100% | Medium | To Do |  |  | 2024/09/02 | 2024/09/02 | 1 | 0% | 2025-12-31
1-16 |  | Debugging | ANEXAS-13 | Epic | Umar Waqar | 100% | Medium | In Progress |  |  | 2024/12/23 | 2024/12/31 | 7 | 0% | 2025-08-20
1-16-1 |  | Debugging | ANEXAS-10 | Task | Ali Zaman Kayani | 100% | Medium | To Do |  |  | 2024/12/23 |  | 0 | 0% | 2025-12-31
1-15 |  | Demonstration | ANEXAS-15 | Epic | Ali Zaman Kayani | 100% | Medium | To Do |  |  | 2025/01/08 | 2025/01/08 | 1 | 0% | 2025-09-20
1-7 |  | Iterations (If any) | ANEXAS-26 | Epic | Umar Waqar | 100% | Medium | In Progress |  |  | 2025/01/15 | 2025/01/31 | 13 | 0% | 2025-09-30
1-8 |  | Implementation | ANEXAS-16 | Epic | Umar Waqar | 100% | Medium | In Progress |  |  | 2025/02/03 | 2025/02/14 | 10 | 0% | 2025-09-10
1-6 |  | Pilotting | ANEXAS-17 | Epic | Ali Zaman Kayani | 100% | Medium | To Do |  |  | 2025/02/17 | 2025/02/21 | 5 | 0% | 2025-10-10
1-9 |  | Handover | ANEXAS-30 | Epic | Ali Zaman Kayani | 100% | Medium | To Do |  |  | 2025/02/24 | 2025/02/28 | 5 | 0% | 2025-11-30
1-9-1 |  | Defense | ANEXAS-92 | Task | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-12-15
1-9-2 |  | Language Support - Multiple Languages | ANEXAS-97 | Task | Ali Zaman Kayani | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2025-12-20